## Introduction
Contents | Project Plan Update the Gantt Chart: Begin by updating the dates. Fill in the Project Management Table: Add actions, descriptions, responsible persons, progress status, start and end dates. Use the grid to visually represent the timeline by shading cells between start and end dates. | Retrofit Project Team Assign Roles: Define who will be the Project Sponsor, Project Director, Project Manager, and Project Team. Specify who is covering each role and their expected time input. Role Descriptions: Provided to clarify responsibilities and expectations.
Retrofit Project Plan
Retrofit Project Team
Risk Register
Actions Log
General Tips Start with the Project Plan tab to map out your timeline and key activities. Use the Team tab to ensure roles are clearly assigned and responsibilities are understood. Regularly update the Risk Register and Actions Log to monitor progress and mitigate issues. Customise the template with your organization’s name and relevant details.
| Risk Register Document Risks: Capture potential risks including fraud risks. Fill in details like risk title, category, description, owner, mitigation, target date, progress, and RAG rating. Example Provided: Helps guide how to fill in the register. | Actions Log Track Actions: Log all actions needed to support project development. Include action number, description, category, date raised, responsible person, target date, and progress.
Retrofit Planning Tool- [Insert Organisation Name]
This document provides a template to support the development of your retrofit project. It is a starter checklist to ensure you are prepared for delivery at the planning phase of your project. It should be used alongside, not replace, a comprehensive project plan that encompasses the delivery of each project phase.
Document author - Support Manager Name
Date of creation / update
Funded by
Document author - Support Manager
[Insert Name]
[Insert date of creation / update]

## Retrofit Project Plan
Retrofit Project Plan
| Project Start: [do not change] | [5 empty] | Date last amended: |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE!
| Date last amended: | [5 empty] | Date last amended: | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Action | Description | Who | Progress | Start | End | M | T | W | T | F | M | T | W | T | F | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Plan
Project management
| RISE regular catch-up | Catch-up with RISE Support Manager to review project development progress
| Kick-off meeting | Gather project team to discuss objectives, timelines, responsibilities and risks
| Project team meeting | Regular catch-up with project team
| Value setting workshops | Value setting workshops to align priorities
| Senior Exec Committee sign-off | Send draft proposal for senior executive committee sign-off.
| Add any additional governance sign-offs | Include any additional sign-offs required
Data analysis & project identification
| Baseline data energy performance data | EPC, heating demand (kWh/m2/year), estimated fuel bills and CO2 emissions for your homes.
| Review data quality | Review data quality and make any data improvements
| Data validation [optional] | Consider collecting additional data through more recent detail energy assessments and/or PAS2035 retrofit assessments.
Retrofit measures & costs
| Model retrofit measure scenarios | Model scenarios to achieve desired performance objectives, this includes understanding expected energy performances |  |  | 2025-01-01 | 2026-02-28
| Review planning requirements | Engage with your planning authority(s) for timelines on any planning permissions required
| Obtain local quotes from suppliers | Get some up to date cost estimates for your measures
| Calculate co-funding | Review final costs, and estimated split between capital and A&A costs
Delivery assurance
| Lessons learnt | Conduct a lessons learnt workshop with relevant teams from previous retrofit delivery
| Resource evidence | Team resource organogram detailing FTE capacity or description of hiring or outsourcing intent
| General assurance | Ongoing contract management and quality assurance framework
| Delivery project plan | Map the project stages and estimated timeframe in-line with policy, add milestones, dependencies and cashflow.
| Project team & resource | Map the resource and skills required for each project stage and task and assign roles
| Risk management | Create a risk management system and risk assessment detailing cause, impact, likelihood, severity and mitigation
| Fraud risk management plan | Develop a fraud risk management plan
Procurement
| Outline route to procurement | Engage with your asset and procurement team to identify a preferred route to procurement for your retrofit project.
| Soft market testing | Draft specification to carry out soft-market testing
| Procurement evidence | Copy of contract confirmation, evidence of invitation to tender
| Invitation to tender preparation | Work on your desired requirements for the tender
Resident engagement
| Review existing approach | Review what resident engagement services you already cover, what has worked and what needs to be updated. Opportunity to hold an additional lessons learnt workshop focused on resident engagement.
| Create a strategy | Create a strategy of how you plan to approach resident engagement. What are your values, timelines, objectives and milestones
| Plan customer journey | Map out each stage and who does what for each stage
| Plan engagement resource | Map what resources activities are required

## Retrofit Project Team
Retrofit Project Team
Assigning your retrofit project team
Roles and Responsibilities | Who is covering this role | Expected time input
Project Sponsor
- works with the Project Director and is accountable for obtaining senior level buy-in for the project - decides and develops the project team with the Project Director - agrees the strategy, direction, and projects requiring funding - reviews and makes decisions related to the project during Gateway Approvals
Project Director
- accountable for project delivery - selects the project team, in discussion with the Project Sponsor - sets the strategy, direction and projects requiring funding - leads, motivates, organises, communicates, allocates tasks
Project Manager
- drives the project process and activities - supports the Project Director in managing the project - liaises and coordinates the Project Team - implements the project timeline and follows up on actions - responsible for ensuring project is delivered to agreed scope
Project Team (including partner organisations and service provider)
- responsible for delivering project outputs - provides specific skills required to deliver project (e.g., technical, financial, legal)

## Risk Register
Project Risk Register
This risk register is to capture and document any potential risks during the development of your retrofit project. Fraud risks may also be included to prepare for formal delivery risk register.
Risk Number | Risk title | Risk category | Date risk raised | Risk description | Risk Owner | Mitigation | Target completion date | Progress | RAG rating
Example risk | No modelling software | Data analysis | 2024-05-21 | No modelling software in place to identify retrofit measures for homes. | Billy Cliffen | Someone contact Software provider for a quote to procuretheir modelling system | 2024-05-28 | Not started | Red
1
2
3
4
5
6
7
8

## Actions Log
Actions Log
This is to capture actions to support in developing your retrofit project.
Action number | Action | Category | Date raised | Responsible | Target completion date | Progress | Complete
Example action | Contact software providers for quotes to procure energy modelling facility | Data analysis | 2024-06-01 | Joanne Bloggs | 2025-06-15 | Emailed three providers with scope of requirement, asking for a quote by 15/06
1
2
3
4
5
6
7
8

## RISE support accessed
RISE support accessed
| Activity | Notes | Date accessed
| Accessed the data for retrofit projects toolkit | Understand the importance of data quality and maintaining datasets so they're current, so it is useful as a basis for costed energy modelling. | 2024-05-25