## Guidance
This example Gantt chart was uploaded to the RISE website in March 2025. It provides an amendable template that retrofit project managers can download and use to map out their project. The stages, actions and sub-actions suggested in this document are unlikely to be applicable to all, but should provide a useful starting point. Please note that the 'establish project team' stage has been populated to demonstrate how to use the template. These are also unlikely to be applicable to every project. Users may also need to add further dates.

## Example Gantt
| Milestones | [5 empty] | Forecast |  |  | March (week commencing) |  |  |  |  | April (W/C) |  |  |  | May (W/C) |  |  |  | June (W/C)
Line ID | Project Stage | Action | Sub Action | Owner | Notes | Frequency | Start Date | End Date | Duration | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
1 | Establish Project Team | Hire vacant roles | Vacancies recruited to internal project team | Name or team name | If applicable | One off or set intervals | 2025-03-03 | 2025-03-10 | 2 weeks
2 |  |  | Vacancies onboarding / initial training |  |  |  | 2025-03-10 | 2025-03-17 | X weeks
3 |  | Project kick off | Team established, governance and reporting aligned to company guidelines |  |  |  | 2025-03-17 | 2025-03-31 | 2 weeks
4 |  |  | Data sharing protocols agreed with delivery partners |  |  |  | 2025-03-17 | 2025-03-31 | 2 weeks
5 |  | Internal Governance | Establish organisation-specific controls |  |  |  | 2025-03-31 | 2025-04-14 | 3 weeks
6
6 | Procurement Activity | Contractor Engagement | Procurement exercise for existing contract extensions commences (if necessary) | Name or team name | If applicable | One off or set intervals |  |  | X weeks
7 |  |  | Contractor(s) pre-start meeting(s)
8 |  |  | Schedule of works and milestones agreed (or reaffirmed with existing contractors)
9 |  | Contractor Governance | Execution of contract and governance agreed in line with project plan
10 |  |  | Contractor governance and contract management meetings
11 |  |  | Contractor capacity and market supply review for measures - issues and gaps identified
12 | Pre-construction Resident Engagement | Introductory resident engagement | Introductory letter issued to affected residents | Name or team name | If applicable | One off or set intervals |  |  | X weeks
13 |  | Follow up engagement and queries | Pre-work soft engagement event(s)
14 |  |  | Access granted to digital platform pilot for selected residents
15 |  |  | Follow up calls arranged to address specific queries
16 |  |  | Schedule of works shared with contact methods
17 |  | Refusals | Early resident refusals reported and substitute properties identified
18 | Risk Assessment | Property Survey | Sample surveys to identify the best approach and establish current conditions | Name or team name | If applicable | One off or set intervals |  |  | X weeks
19 |  |  | Refine measures list based on survey results
20 |  | Finance modelling | Financial model complete
21 |  | Pre-work assessment and actions | Scope of works and specification written by the project designer
22 |  |  | Pre-installation monitoring and evaluation commences
23 |  |  | Complete dwelling assessments, identify risk paths per type and develop medium term improvement plans per risk path
24 |  |  | Complete planning and building control requirements - permissions, ecology surveys etc.
25 |  |  | Identify problem properties and substitute, as required
26 | Design and Coordination | Procurement Strategy | Procurement strategy and works timescales confirmed - report of improvement options evaluation submitted | Name or team name | If applicable | One off or set intervals |  |  | X weeks
27 |  | Resident Engagement for design | Share visualisations and information packs with affected residents (optional online platform pilot, where applicable)
28 |  |  | Further on site resident engagement and follow up calls to address any specific queries
29 |  |  | New resident refusals reported and substitute properties identified, additional support and guidance offered with contractors
30 | Instillation | Instillation | Works on site (broken down into organisational workstreams where relevant) | Name or team name | If applicable | One off or set intervals |  |  | X weeks
31 |  |  | Draw down of funds
32 |  |  | Resident in-home energy advice service commences
33 |  |  | Installation of clean heat or energy solutions, if not specified in the bid?
34 |  | Post-instillation | Post works inspection and sign off by Retrofit Coordinator
35 |  |  | Post works inspection and sign off by contractor's QA function
36 |  |  | Any final draw down of funds outstanding
37 | Handover and data lodgement | Post-instillation monitoring | Post installation monitoring and evaluation commences | Name or team name | If applicable | One off or set intervals |  |  | X weeks
38 |  |  | Identify performance gaps, or unintended consequences and remedy
39 |  | Resident handover | Resident handover, system demonstration, in home energy advice follow up and tariff setting checks - income maximisation referral to the Financial Inclusion Team as required
40 |  |  | Resident feedback event and satisfaction survey issued
41 |  | Handover complete | Post installation monitoring and evaluation ends or moves into BAU
42 |  |  | All works are logged with Trust Mark or equivalent
43 |  |  | Internal systems updated accordingly and evidence retained
44 |  | Project close | Project close out report completed and reviewed for lessons